## Sheet1
Task | Deliverable | Start Date | End Date | Assigned | 2026-02-05 | 2026-02-06 | 2026-02-07 | 2026-02-08 | 2026-02-09 | 2026-02-10 | 2026-02-11 | 2026-02-12 | 2026-02-13 | 2026-02-14 | 2026-02-15 | 2026-02-16 | 2026-02-17 | 2026-02-18 | 2026-02-19 | 2026-02-20 | 2026-02-21 | 2026-02-22 | 2026-02-23 | 2026-02-24 | 2026-02-25 | 2026-02-26 | 2026-02-27 | 2026-02-28 | 2026-03-01 | 2026-03-02 | 2026-03-03 | 2026-03-04 | 2026-03-05 | 2026-03-06 | 2026-03-07 | 2026-03-08 | 2026-03-09 | 2026-03-10 | 2026-03-11 | 2026-03-12 | 2026-03-13 | 2026-03-14 | 2026-03-15 | 2026-03-16 | 2026-03-17 | 2026-03-18 | 2026-03-19 | 2026-03-20 | 2026-03-21 | 2026-03-22 | 2026-03-23 | 2026-03-24 | 2026-03-25 | 2026-03-26 | 2026-03-27 | 2026-03-28 | 2026-03-29 | 2026-03-30 | 2026-03-31 | 2026-04-01 | 2026-04-02 | 2026-04-03 | 2026-04-04 | 2026-04-05 | 2026-04-06 | 2026-04-07 | 2026-04-08 | 2026-04-09 | 2026-04-10 | 2026-04-11 | 2026-04-12 | 2026-04-13 | 2026-04-14 | 2026-04-15 | 2026-04-16 | 2026-04-17 | 2026-04-18 | 2026-04-19 | 2026-04-20 | 2026-04-21 | 2026-04-22
Finalize project requirements and design decisions | Design notes | 2026-02-05 | 2026-02-07 | Ibrahim & Evan
Implement custom hash table (insert, search, delete) | HashTable.cpp | 2026-02-08 | 2026-02-14 | Evan
Implement word filtering logic using feedback rules | Filter module | 2026-02-10 | 2026-02-18 | Ibrahim
Build command-line menu interface | CLI prototype | 2026-02-15 | 2026-02-20 | Ibrahim
Unit testing for hash table (30 test cases) | Test table | 2026-02-18 | 2026-02-24 | Evan
Implement tree structure for guess paths | Tree.cpp | 2026-02-26 | 2026-03-05 | Evan
Implement greedy guess selection algorithm | GreedySolver.cpp | 2026-03-01 | 2026-03-10 | Ibrahim
Integration testing and debugging | Updated test results | 2026-03-08 | 2026-03-20 | Ibrahim & Evan
Implement backtracking algorithm | BacktrackingSolver.cpp | 2026-03-15 | 2026-03-25 | Evan
Final testing (100+ test cases) | Final test report | 2026-03-26 | 2026-04-10 | Ibrahim & Evan
Final report writing | Final paper | 2026-04-10 | 2026-04-20 | Evan
Presentation slides and demo prep | Slides + demo | 2026-04-15 | 2026-04-22 | Ibrahim